# Deliverables for LunaNet

- Gateway based approach where each gateway represents a functional capability requirement

## Key dates

- 18-19th June, 2 day workshop at goon hilly earth station, Cornwall, UK

- 31st August submission deadline

## Suggested Timeline

Sure! Here's the gateway section as a table:

| Gateway | Name | Target | Goal | Scoring Weight |
| --- | --- | --- | --- | --- |
| 0 | Design & Architecture | April 2026 | Design system architecture and establish development foundation | Not scored directly |
| 1 | Spreading Code Generation | May 2026 | Generate all spreading codes (Gold, Weil, Secondary) for PRN 1–210 | 10 pts (Correctness) |
| 2 | Forward Error Correction | June 2026 | Implement BCH, LDPC, and CRC-24 encoders/decoders (Error detector codes) | Part of 10 pts (Correctness) |
| 3 | Navigation Message Framing | June 2026 | Build complete 12-second navigation frames | Part of 10 pts (Correctness) |
| 4 | Baseband Signal Generation | July 2026 | Generate I/Q baseband samples (represent complex radio waves as numerical data) with BPSK modulation (converts binary data to radio/light waves) | Part of 10 pts (Correctness) |
| 5 | Frame Sync & Decoding | August 2026 | Detect and decode frames from received signals | Part of 10 pts (Correctness) |
| 6 | Message Parsing | August 2026 | Extract navigation data from decoded frames | Not scored directly |
| 7 | Integration & Validation | August 2026 | End-to-end functionality, interoperability, and compliance | Across all categories |
| 8 | Documentation & Examples | August 2026 | Complete documentation for using and understanding the implementation | Code Quality (10 pts) |

## Scoring Overview

| Category | Points |
| --- | --- |
| Correctness | 40 |
| Performance | 20 |
| Completeness | 20 |
| Code Quality | 10 |
| Innovation and Extras | 10 |

## Deliverables Checklist

Here’s the deliverables expected at each gateway:

Gateway 0 – Design & Architecture

- System architecture document

- Component interaction diagrams

- Technology stack selection

- Development environment setup

- Testing strategy and framework

- Code structure and module design

- Interface definitions

- Data format specifications

Gateway 1 – Spreading Code Generation

- Gold code generator (2046-chip codes, PRN 1–210)

- Legendre sequence generator

- Weil primary code generator (10230-chip codes, PRN 1–210)

- Weil tertiary code generator (1500-chip codes, PRN 1–210)

- Secondary code generator (4 chips, 4 variants)

- Tiered code assembly with coherent generation

- Validation against Annex3 reference codes

- Test suite covering all 210 PRN codes

Gateway 2 – Forward Error Correction

- BCH (51,8) encoder and decoder

- CRC-24 generator and validator

- LDPC encoder and decoder (rate 1/2) for SB2, SB3, SB4

- Block interleaver and deinterleaver (60×98)

- Test vectors for each encoder

Gateway 3 – Navigation Message Framing

- Synchronisation pattern generator (68 symbols)

- Subframe 1 builder (FID + TOI, BCH encoded)

- Subframe 2 builder (Clock & Ephemeris, LDPC encoded)

- Subframe 3 builder (Variable data, LDPC encoded)

- Subframe 4 builder (Network access, LDPC encoded)

- Frame assembler with sync pattern

- Complete 12-second frame generator

- Frame export in multiple formats

Gateway 4 – Baseband Signal Generation

- Tiered code assembly (primary + secondary + tertiary)

- BPSK modulator for AFS-I (1.023 Mchip/s)

- BPSK modulator for AFS-Q (5.115 Mchip/s)

- I/Q sample generator with configurable sample rate

- Code synchronisation implementation

- Signal file export (binary, CSV)

Gateway 5 – Frame Synchronisation & Decoding

- Frame synchronisation via sync pattern detection

- Symbol extraction from I/Q samples

- BCH (51,8) soft-decision decoder

- LDPC belief propagation decoder

- CRC validator

- Block deinterleaver

Gateway 6 – Message Parsing

- Subframe 1 parser (FID + TOI extraction)

- Subframe 2 parser (Clock & Ephemeris)

- Subframe 3 parser (Variable data routing)

- Subframe 4 parser (Network access)

- Time of Transmission calculator

- Message field extractors for all fields

Gateway 7 – Integration & Validation

- Round-trip tests (encode → signal → decode → verify)

- Interoperability test results with other implementations

- Performance benchmarks (throughput, latency)

- Compliance validation report

- Test vector suite

- BER vs SNR performance curves

Gateway 8 – Documentation & Examples

- README with project overview

- Setup and build instructions (reproducible)

- API documentation

- Usage examples for all components

- Design documentation with architecture decisions

- Test documentation and how to run tests

- Performance analysis report

## Validation Checklist

Here's a simplified validation checklist for each gateway:

Gateway 0 – Design & Architecture

- Clear architecture with defined components

- Development environment is ready and working

- Testing framework established

- Team aligned on approach

Gateway 1 – Spreading Code Generation

- Gold codes for all 210 PRNs match Annex3 hex references exactly

- Weil primary codes for all 210 PRNs match Annex3 references exactly

- Weil tertiary codes for all 210 PRNs match Annex3 references exactly

- Secondary codes match Table 10

- Tiered codes maintain coherency

- Code lengths match Table 9 specifications

- All 12 interim test codes (Table 11) working

- Code generation completes in under 1 second per PRN

Gateway 2 – Forward Error Correction

- BCH encoder produces valid 52-symbol codewords

- LDPC encoder produces valid codewords and handles puncturing correctly

- CRC-24 computation matches specification

- Interleaver pattern validated

- Decoders recover original data via round-trip

- BER < 10⁻⁵ at SNR > 0 dB

- Encoding completes in under 100ms per frame

- Decoding completes in under 1 second per frame

Gateway 3 – Navigation Message Framing

- Frame structure matches Figure 9

- Symbol counts correct: 68 + 52 + 5880 = 6000

- Bit allocations match specification tables

- Frame duration is exactly 12 seconds

Gateway 4 – Baseband Signal Generation

- I/Q samples correctly formatted

- Chip rate is 1.023 Mchip/s for AFS-I

- Chip rate is 5.115 Mchip/s for AFS-Q

- Symbol rate is 500 symbols/s for AFS-I

- Code synchronisation meets specification

- Signal duration matches frame duration (12 seconds)

Gateway 5 – Frame Synchronisation & Decoding

- Frame sync detection above 99% at SNR > 0 dB

- Decoders recover original data correctly

- CRC validation catches errors

- LDPC decoder converges in under 50 iterations

- Frames decoded in under 1 second

Gateway 6 – Message Parsing

- All subframes parse correctly

- WN, ITOW, and TOI fields extracted

- Time of transmission calculated accurately

- Time reconstruction accurate to code phase

- All message types in SB3/SB4 handled

Gateway 7 – Integration & Validation

- Round-trip recovers original data with 100% accuracy

- All performance (NFR-1) targets met

- All 12 interim test codes (Table 11) working

- All specification "shall" requirements verified

- Interoperability with at least one other implementation demonstrated

Gateway 8 – Documentation & Examples

- Setup instructions complete — anyone can build and run from scratch

- Usage examples work and demonstrate key functionality

- All public APIs documented

- Tests documented with instructions to reproduce

- All dependencies documented or included

## Final Submission

When finally submitting these are all required:

- Complete source code

- Build/setup instructions

- Test suite with results

- Documentation

- Examples demonstrating functionality

- Validation report showing compliance